## Sprint
Sprint: {{title: team, sprint number, start and end dates}}
Sprint goal: |  | {{goal: sprint goal and why it matters now}}
Product goal: |  | {{product_goal: what the sprint leads towards}}
Sprint limit: |  |  | {{unit: estimate unit}} |  | Goal achieved:
Review outcome: |  | {{review: what was shown and decided next}}
# | Item | For the goal | How we will do it | Who | Estimate | Source | Done | What next | Sprint results
Items
Of them for the goal
Taken at planning
Load vs limit
Added during the sprint
Not done
Share unfinished
Goal items not done
Note on C4: How much the team is ready to take, in the units of the "Estimate" column: capacity accounting for time off and the results of past sprints. A guide, not a hard limit.
Note on G4: Filled in at the sprint review: yes, partly or no.
Note on A7: Calculated automatically.
Note on B7: An item from the product's shared work list, taken into the sprint. The most important at the top.
Note on C7: "yes" — the item is needed for the sprint goal. The other items are done if there is capacity.
Note on D7: The plan: subtasks or steps to a finished result.
Note on E7: Who takes the item. The team distributes the work itself.
Note on F7: An estimate by those who will do the work, in the units from row 4.
Note on G7: "planned" — taken at planning; "added" — came in during the sprint.
Note on H7: "yes" — the item meets the team's definition of done. Filled in at the end of the sprint.
Note on I7: For unfinished items: return to the shared list, carry over to the next sprint, cancel — and why.
Note on K8: How many items are in the sprint.
Note on K9: Zero — there is no goal, the sprint became a task list. All — the goal most likely just restates the items.
Note on K10: The sum of estimates of "planned" items.
Note on K11: What was taken at planning divided by the limit. Above 100% — the team promises more than it has delivered before.
Note on K12: Work that arrived after planning. Its volume hints at how much reserve to leave.
Note on K13: The sum of estimates of items without "yes" in the "Done" column.
Note on K14: Not done divided by everything taken and added.
Note on K15: More than zero at the end of the sprint — the goal is at risk, even if the rest is done.

## History
Sprint history
Sprint | Sprint goal | Goal achieved | Limit | Taken | Added | Not done | Done | Share unfinished | All done | Over the last 10 sprints
Sprints in history
Goal achieved
Everything taken was done
Note on A4: Number or dates.
Note on B4: The goal statement.
Note on C4: yes, partly or no.
Note on D4: The limit the team agreed on at planning.
Note on E4: Taken at planning, in estimate units.
Note on F4: Added during the sprint, including growth of estimates.
Note on G4: Removed from the sprint or not brought to done by its end.
Note on H4: Calculated automatically: taken + added − not done.
Note on I4: Calculated automatically: not done / (taken + added).
Note on J4: Calculated automatically: "yes" if not done is 0.
Note on L5: How many sprints are recorded.
Note on L6: In how many sprints the goal was fully achieved.
Note on L7: The benchmark of M. Cohn as retold by Rosbank: in 8 of the last 10 sprints the team did everything it promised.