## Backlog
Product Backlog: {{title: product, team and snapshot date}}
Product goal: |  | {{goal: product goal for the next months}}
Capacity per sprint: |  |  | {{unit: size unit}}
Rank | Item | Type | Contribution to the goal | Why in this position | Size | Ready for sprint | Requested by | Added | Decision | State of the list
Total items
No contribution to the goal
No size estimate
Ready for sprint
Size of ready items
Ready stock, sprints
Older than 6 months
Marked "delete"
Note on C3: How many size units the team completes on average per sprint — in the same units as the "Size" column. Empty — the stock of ready items in sprints is not counted.
Note on A5: Calculated automatically: the row order. Higher means earlier to work on. The product owner sets the order; two items cannot share a position.
Note on B5: What needs to be done for the product, one row per item. The top of the list holds small, clear items, the bottom large and rough ones.
Note on C5: Feature, bug, technical work, research or requirement.
Note on D5: How the item brings the product goal from row 2 closer. Empty — the item is a candidate for removal.
Note on E5: Value, risk, deadline, dependencies — what put the item above or below its neighbours.
Note on F5: An estimate by those who will do the work, in the units from row 3. Required for the top items.
Note on G5: "yes" — the team is sure it can finish the item in one sprint: it is understood, estimated and not blocked.
Note on H5: The customer or source of the item: users, support, the regulator, the team.
Note on I5: The date the item entered the list. Old items with no movement are candidates for removal.
Note on J5: The outcome of the last review: keep, postpone or delete.
Note on L6: Hundreds or thousands of items are a sign of a dumping ground: the top of the list gets lost.
Note on L7: Items that do not lead to the product goal. Each one raises a question: delete it or change the goal.
Note on L8: The top of the list needs an estimate, for the bottom a rough one is enough.
Note on L9: Items that can be taken into the next planning.
Note on L10: The sum of the sizes of ready items.
Note on L11: The size of ready items divided by capacity. Under one sprint — refine the top of the list before planning.
Note on L12: Items added more than half a year ago. Candidates for review.
Note on L13: Remove them from the list after the review.