## Risk register
Risk Register: {{title: what the register covers, organization or product, and the date}}
Scope: |  | {{scope: the objective or project whose risks are listed, and who reviews the register}}
Decision: |  | {{decision: what the review decided about the top risks: response, escalation or acceptance}}
ID | Risk statement | Cause | Effect | Category | Owner | Likelihood (1-5) | Impact (1-5) | Response type | Response | Status | Date raised | Last reviewed | Next review | Score | Rating | Priority rank | Review flag | Summary
[18 empty] | High from (score) | 15
[18 empty] | Medium from (score) | 6
Risks listed
High, not closed
Medium, not closed
Low, not closed
Closed
Review overdue
Without owner
Without response
Highest score
Formulas:
Review flag = IF(OR([Next review]="",[Status]="Closed"),"",IF([Next review]<TODAY(),"Overdue",""))
Note on A5: Risk identifier: a short code that does not change, for example R-01. Used to refer to the risk in meetings and reports.
Note on B5: The risk as one event that could happen, in common phrasing so rows compare: what could happen to which asset or objective. Not "supplier issues" but "main payment provider is unavailable for more than a day".
Note on C5: What makes the event possible: the threat, weakness or condition behind it.
Note on D5: What happens to the objective if the event occurs: money, customers, schedule, compliance, reputation.
Note on E5: Theme for grouping rows and comparing registers, for example operational, financial, legal, technology, market.
Note on F5: One named person accountable for keeping this risk within agreed limits. A group or "team" is not an owner.
Note on G5: How likely the event is now, with existing controls: 1 rare, 2 unlikely, 3 possible, 4 likely, 5 almost certain. Write the meaning of each level down before scoring.
Note on H5: How severe the effect is now, with existing controls: 1 minor to 5 severe. Define each level in money, customers or delay before scoring.
Note on I5: Accept (monitor only, within tolerance), transfer (share the consequences, for example insurance), mitigate (reduce likelihood or impact), avoid (do not take the action). For opportunities: realize, share, enhance, accept.
Note on J5: What will be done, by whom and by when. For accept, write what is monitored and the trigger to revisit.
Note on K5: Open, In progress (response under way) or Closed (risk ended or the response is complete and the risk is back within limits).
Note on L5: Date the risk was first entered in the register.
Note on M5: Date of the last reassessment of likelihood and impact.
Note on N5: Date by which the risk must be reviewed again. Rows past this date are flagged.
Note on O5: Calculated: likelihood x impact. An ordinal number for ranking, not a probability or a loss.
Note on P5: Calculated: High at or above the High-from score, Medium at or above the Medium-from score, otherwise Low. Bands are set in the summary.
Note on Q5: Calculated: 1 is the highest score among open risks; equal scores share a rank. Closed risks are not ranked.
Note on R5: Calculated: Overdue when the next review date is before today and the risk is not closed.
Note on T6: Score at or above this value is rated High. Set it with your scale and risk appetite; 15 suits a 5 x 5 grid.
Note on T7: Score at or above this value, and below High, is rated Medium; lower is Low.
Note on T8: Rows with a risk statement.
Note on T9: Risks rated High that are not closed.
Note on T10: Risks rated Medium that are not closed.
Note on T11: Risks rated Low that are not closed.
Note on T12: Risks with status Closed.
Note on T13: Open risks whose next review date has passed.
Note on T14: Must be 0: a risk without an owner is nobody's.
Note on T15: Risks with an empty Response column.
Note on T16: The largest score in the register.